## Burn down chart
Release Burndown
Sprints completed | Expected Story Points Remaining | Actual Story Points Remaining
0 | 24 | 24
1 |  | 14
2
3
4 | 0
Sprint 2 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 44 | 44
19 |  | 43
18 |  | 41
17 |  | 40
16 |  | 38
15 |  | 36
14 |  | 33
13 |  | 31
12 |  | 28
11 |  | 25
10
9
8
7
6
5
4
3
2
1
0 | 0
ALSO DO A SPRINT 2 BURNDOWN AS WELL