## Burn down chart
Release Burndown
Sprints completed | Expected Story Points Remaining | Actual Story Points Remaining
0 | 24 | 24
1
2
3
4 | 0
Sprint 1 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 35 | 35
19 |  | 35
18 |  | 33
17 |  | 30
16 |  | 26
15 |  | 26
14 |  | 24
13 |  | 24
12 |  | 24
11 |  | 20
10 |  | 18
9 |  | 17
8 |  | 16
7 |  | 14
6
5
4
3
2
1
0 | 0
ALSO DO A SPRINT 2 BURNDOWN AS WELL