## Burn down chart
Release Burndown
Sprints completed | Expected Story Points Remaining | Actual Story Points Remaining
0 | 24 | 24
1 |  | 14
2
3
4 | 0
Sprint 2 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 58 | 58
19 |  | 57
18 |  | 55
17 |  | 54
16 |  | 52
15 |  | 50
14 |  | 47
13 |  | 45
12 |  | 42
11 |  | 39
10 |  | 34
9 |  | 29
8 |  | 25
7 |  | 22
6 |  | 18
5
4
3
2
1
0 | 0
ALSO DO A SPRINT 2 BURNDOWN AS WELL